## Subject to Approval Projects
CURRENT PROJECTS SUBJECT TO APPROVAL |  | MILESTONES | [12 empty] | DETAILS
PROJECT NAME | DESCRIPTION | PRESENTED TO BOARD | RETAINER SIGNED | RETAINER FUNDED | CONDITION STUDY | FINAL PLAN/IMPACT | BUDGET | PLANNING | PPLD IA | PPLD | BOCC | SEWCD | SCHOOL DISTRICT | CITY COUNCIL | NOTES | PRESS
AMALGRE/LOFTS @ 1609 | Affordable Housing S/E | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-11-01 | 2021-02-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | Nov | 2021-11-21 | 2021-12-21 | COMPLETE! Dev Agreement in front of board | Gazette Article | southeastexpress | KRDO
HANCOCK COMMONS | Attainable Housing w/Commercial S/E | 2021-04-01 | 2021-05-01 | 2021-05-01 | 2021-06-01 | 2021-08-21 | [8 empty] | Studies complete now waiting on land acquisition
WEIDNER / CITYGATE | Market Rate Housing w/Commercial Downtown | 2021-04-01 | 2021-06-01 | 2021-07-01 | 2021-09-21 | 2021-11-21 | [8 empty] | Districts noticed. Condition Study and Draft Plan Complete | Gazette Article | Gazette Article
GAZETTE SF | Market Rate Housing w/Commercial Downtown | 2021-04-01 | [12 empty] | Consultants ready pending retainer | Indy. Article
Gold Hill Commerical | Commercial/Residential development in GHM | 2021-08-21 | 2022-12-21 | 2022-12-21 | 2022-02-22 | 2022-03-22 | [8 empty] | Consultants beginning Condition Study Work
Museum and Park 2 | Boundary expansion and new area | 2022-12-21 | 2022-02-21 | 2021-01-01 | 2022-12-21
Oneil Project | Office/residential project with retail | 2022-10-21 | 2022-12-21

## Current Projects
URA | PROJECT | START | END |  | CONSTRUCTION | PROJECT COMPLETION | NOTES | PRESS
C4C PROJECTS | AFA Visitor Center |  |  | In Progress | Started | 2024 | Bonds Closing Announced | CSBJ Article
| Robson Arena |  |  | Complete | Complete | Complete
| Weidner Field |  |  | Complete | Complete | Complete |  | Gazette Article
| USOPM |  |  | Complete | Complete | Complete |  | CSBJ Article | Indy Article | Gazette Article
| Hybyl Sports Medicine |  |  | Complete | Complete | Complete
MUSEUM & PARK | Residential & Commercial | 2018 | 2043 | Bonds Issued | Infrastructure/Streetscape | TBD | Developer Proceeding with a New Area/Clock. Streetscape/Bridge won the ULI impact reward
CITY AUD BLOCK | Hyatt Hotel | 2004 | 2029 | Complete | OPEN! | Fall 2021 | Another update coming soon | Fox21News | Indy Article | CSBJ Article
GOLD HILL MESA | Residential | 2004 | 2029 | Complete | In Progress | Fall 2021 | Working through filings 10 (soon) & 11 (Fall 2021) | Indy Article | Fox 21
| Commercial | 2015 | 2040 | No | In Progress | TBD | Consultants are doing study work for new area/clock
IVYWILD |  | 2011 | 2036 | Complete | Complete | Complete* | * Ivywild School and Blue Star will both have updates soon
N. NEVADA AVE |  | 2015 | 2040 | Complete | Complete* | Complete* | Bonds refinanced January 2021 * Lexus Building Commencing soon | Gazette Article
POLARIS POINTE |  | 2010 | 2035 | Complete | In Progress | Fall 2021/Spring 2022 | New area developer update coming soon | Gazette Article
TEJON & COSTILLA |  | 2018 | 2043 | Complete | In Progress | Spring 2022 | Developer interested in scheduling a board tour January | Gazette Article
TRUE NORTH COMMONS |  | 2019 | 2044 | No (see AFA) | Not Started | TBD
VINEYARD |  | 2011 | 2036 | Complete | Complete* | Complete*
S. NEVADA | EVC-HD |  |  | Complete | Complete | Complete | Developer has shown interest in securing other sites on east side if TIF available. | CSBJ Article
| Ivywild LLC |  |  | Complete | In Progress | Late 2022 (estimated) | Hotel, restaurant and added residential going through 2022 | CSBJ Article 2
| Canyon Creek LLC |  |  | Ongoing | In Progress | Late 2022 (estimated) | Council passed sales tax increase to 2% Heavy site work and creek work has begun | KRDO Story